## Day0_Execution_Plan
0 | Day | Target Start (CST) | Target Finish (CST) | Task Description | Responsibility | Resource Name | Status | Comment | Actual Start | Actual Finish | Actual Duration
Pre-requisite
-10 | Day - |  |  | Apply all Saviynt patches : JIRA# SD-25026 : After AD Entitlement recon, owners are getting deleted from entitlement. database 'wait_timeout' setting is configured #687436 Access Query column size is small to store big query #644733 Trigger Chain Sequence | Saviynt |  | Completed
| Day -3 | 01/05/2021 6.30 AM | 01/07/2021 6.30 AM | Upload HCM Utility jar from UAT to Production. This Jar has the pre-processor code which performs the user data transformation before loading HCM data into Saviynt. | Saviynt/KPMG | Sahaj Ranajee/Ajinkya Chavan | Pending | Ajinkya to sync with Saviynt on 5th Jan
| Day - |  |  | Migrate all UI and Branding changes from UAT to Production | Saviynt |  | Completed
| Day - |  |  | Update message.properties in Production from UAT | Saviynt |  | Completed
| Day - |  |  | Get Saviynt DB User Name and Password | Saviynt |  | Completed
| Day - |  |  | Import Active Directory SSL Certificate in Saviynt environment to allow SSL connection from Saviynt to Active Directory | KPMG/Saviynt |  | Completed
| Day -2 | 01/06/2021 7.30 AM | 01/06/2021 8.00 AM | Get the User account, Password for Active Directory (This account should have Administrator rights for Windows server access). This account will be used in Saviynt to perform all CRUD operation in Active Directory and to reconcile User account and Active Directory group. | Hormel | Nate Hosper | Pending | Nate Hosper
| Day - |  |  | Get Production HCM url, User Name and Password This account will be used in Saviynt to reconcile Users from HCM. | Hormel |  | Completed | Setup call with Hormel HCM team to update the password in new connection
| Day - |  |  | Get IP Address, User Name and Password of window connect server where Saviynt Application is installed, which will be used to call PowerShell script for Mailbox. | Hormel |  | Completed | Setup call with Nathan to stamp the AD user password for Mailbox recon
| Day - |  |  | Get the list of users for ROLE_HORMEL_ADMIN : Jane E Wall (JEWALL) Debra L Irish (DLIRISH) Laura J Zahradnik (LJZAHRADNIK) | Hormel |  | Completed
| Day - |  |  | Get the list of users for ROLE_HORMEL_HELPDESK | Hormel |  | Completed
| Day - |  |  | Get the list of users for ROLE_ADMIN : Wesley E Rowden (WEROWDEN) Henry D Kasper (HDKASPER) Chad L Dahlberg (CLDAHLBERG) | Hormel |  | Completed
| Day - |  |  | Get the DL's for Active Directory Admin Team, Mailbox Admin Team, Security Techs Team | Hormel |  | Completed | "SecurityTech@hormel.com", "emailsecadmin@hormel.com”, "ITS_Wintel_Systems_Programmers@hormel.com"
| Day -1 | 01/08/2021 5.30 PM | 01/08/2021 6.00 PM | Get csv from Active Directory for all Hormel Users using below query : Get-ADUser -Filter * -Properties displayName,sAMAccountName,employeeNumber,userAccountControl,mail,givenName,initials,sn¦ Where-Object {` ($_.DistinguishedName -like "*OU=Users,*") -and ` ($_.DistinguishedName -notlike "*OU=Restricted,*") -and ` ($_.DistinguishedName -notlike "*OU=Departmental Units,*") -and ` ($_.DistinguishedName -notlike "*OU=Farms,*") -and ` ($_.DistinguishedName -notlike "*OU=GenericUsersMailEnabled,*") -and ` ($_.DistinguishedName -notlike "*OU=NVR,*") -and ` ($_.DistinguishedName -notlike "*OU=PCAutoLockTesting,*") -and ` ($_.DistinguishedName -notlike "*OU=Plant accounts,*") -and ` ($_.DistinguishedName -notlike "*OU=Vendors,*") } ¦ Export-csv C:\User.csv | Hormel | Nate Hosper/Tony Bowe | Pending | Nate Hosper
| Day -1 | 01/08/2021 5.30 PM | 01/08/2021 6.00 PM | Get the all user from HCM in required format | Hormel | Mary Tauger | Pending | Mary Tauger
Change Management/ End User Training
| Day - |  |  | End User Training | Hormel/KPMG | Chad Dahlberg/Wesley Rowden/Anjali Patil | Completed
| Day -1 | 01/08/2021 5.30 PM | 01/08/2021 6.00 PM | Turn Off Active Directory Scripts | Hormel/KPMG | Nate Hosper/Tony Bowe | Pending | Nate Hosper/Tony Bowe
| Day -1 | 01/08/2021 5.30 PM | 01/08/2021 6.00 PM | Turn Off Mailbox Scripts | Hormel/KPMG | Nate Hosper/Tony Bowe/Mark Burnett/Douglas Broeren | Pending | Nate Hosper/Tony Bowe
Deployment
| Day - |  |  | Saviynt artifact deployment on production as per the configuration document. | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Completed
| Day -3 | 01/05/2021 6.30 AM | 01/06/2021 6.30 AM | Configure DL's in email templates | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
| Day -2 | 01/06/2021 7.30 AM | 01/06/2021 8.00 AM | Windows Agent installation | Hormel | Nate Hosper | Pending | Confirm the Prod IP address
Validation
| Day -3 | 01/05/2021 6.30 AM | 01/06/2021 6.30 AM | Validate all request form in Saviynt ARS page | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
User and Account Load
| Day 0 | 01/08/2021 5.00 PM | 01/08/2021 5.30 PM | Receive latest files from Oracle HCM team for Employee and Contractor user records in required format | KPMG/Hormel | Vineet Gupta/Mary Tauger | Pending
| Day 0 | 01/08/2021 7.30 PM | 01/08/2021 7.40 PM | Remove Initiate Provisioning Rule job from Employee Recon Job chain | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
| Day 0 | 01/08/2021 7.40 PM | 01/08/2021 7.50 PM | Remove the Provisioning trigger job schedule | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
| Day 0 | 01/08/2021 7.50 PM | 01/08/2021 8.10 PM | Run and Schedule the job for daily run for Oracle HCM Country account recon | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
| Day 0 | 01/08/2021 8.10 PM | 01/08/2021 8.30 PM | Run and Schedule the job for daily run for Oracle HCM JobName account recon | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
| Day 0 | 01/08/2021 8.30 PM | 01/08/2021 8.50 PM | Run and Schedule the job for daily run for Oracle HCM Location account recon | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
| Day 0 | 01/08/2021 8.50 PM | 01/08/2021 9.10 PM | Run and Schedule the job for daily run for Run Active Directory Entitlement reconciliation | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
| Day 0 | 01/08/2021 9.10 PM | 01/08/2021 10.30 PM | Upload Active Directory Users from CSV | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
| Day 0 | 01/08/2021 10.30 PM | 01/09/2021 02.00 AM | Upload the users from HCM CSV | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
| Day 0 | 01/09/2021 02.00 AM | 01/09/2021 02.30 AM | Run and Schedule the job Active Directory User reconciliation (AD_USER_IMPORT_RECON) for daily run | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
| Day 0 | 01/09/2021 02.30 AM | 01/09/2021 03.00 AM | Run and Schedule the job for daily run for Saviynt Security System Target reconciliation | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
| Day 0 | 01/09/2021 03.00 AM | 01/09/2021 03.30 AM | Run and Schedule the job for daily run for HCM User Recon | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
| Day 0 | 01/09/2021 03.30 AM | 01/09/2021 04.00 AM | Run and Schedule the job for daily run for Active Directory Target reconciliation | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
| Day 0 | 01/09/2021 04.00 AM | 01/09/2021 04.30 AM | Run and Schedule the job ACTIVE_DIRECTORY_OU_UPDATE for daily run | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
| Day 0 | 01/09/2021 04.30 AM | 01/09/2021 05.00 AM | Run and Schedule the job for daily run for Mailbox Target reconciliation | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
| Day 0 | 01/09/2021 05.00 AM | 01/09/2021 05.30 AM | Run the job MANAGER_UPDATE_RECON | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
| Day 0 | 01/09/2021 05.30 AM | 01/09/2021 06.00 AM | Run the job LOCATION_UPDATE_RECON | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
| Day 0 | 01/09/2021 06.00 AM | 01/09/2021 06.30 AM | Run the job JOBNAME_UPDATE_RECON | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
| Day 0 | 01/09/2021 06.30 AM | 01/09/2021 07.00 AM | Run the job COUNTRY_UPDATE_RECON | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
| Day 0 | 01/09/2021 07.00 AM | 01/09/2021 07.30 AM | Run and Schedule the job EMAIL_DOMAIN_UPDATE for daily run | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
| Day 0 | 01/09/2021 07.30 AM | 01/09/2021 08.00 AM | Run and Schedule the job NAME_ATTRIBUTE_SYNC for daily run | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
| Day 0 | 01/09/2021 08.00 AM | 01/09/2021 08.30 AM | Add Jewall, dlirish, ljzahradnik, cldahlberg, werowden & hdkasper to Hormel Approval Group | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
| Day 0 | 01/09/2021 08.30 AM | 01/09/2021 09.00 AM | Add IEANDERSON,SLBOGNAR,CLLARSON,JJHULLANDER,SSALINAS,LMHARBER,MJSTEEN,KMLUTZ,EMELBY,MQUETZECUA,MJSTIEHM,ZMCHANDLER,DAWINTERSCHEID,HAOSBERG,MRWEINMANN,DDHOTOPP,DLLERUM,BDLEISEN,BLHOLMQUIST,JEWALL,DLIRISH,LJZAHRADNIK,HDKASPER Our L2 group David Price - DJPRICE Omar Jauregui OEJAUREGUI Bruce Loveland BALOVELAND Ryan Lundberg RCLUNDBERG Benjamin Reburn BBREBURN Juan A. Medinaortiz JAMEDINAORTIZ Additional L1 person Jesus Cisnerospizarro JCISNEROSPIZARRO to HORMEL_HELPDESK_ROLE SAV Role | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
Go - No Go Decision
| Day 0 | 01/09/2021 10.00 AM | 01/09/2021 10.30 AM | Decision of Go - No Go Live | Hormel |  | Pending | Steering Committee
Go-Live
| Day 1 | 01/09/2021 10.30 AM | 01/09/2021 10.45 AM | Schedule Provisioning trigger job | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
| Day 1 | 01/09/2021 10.45 AM | 01/09/2021 11.00 AM | Schedule HCM User trusted recon | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
| Day 1 | 01/09/2021 11.00 AM | 01/09/2021 11.10 AM | Schedule Analytics report | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
| Day 1 | 01/09/2021 11.10 AM | 01/09/2021 11.20 AM | Schedule Mailbox Birth Right reconciliation job (BIRTHRIGHT_MAILBOX_RECON) | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
| Day 1 | 01/09/2021 11.20 AM | 01/09/2021 11.30 AM | Schedule Email History and Request Expiry Job | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending
| Day 1 | 01/09/2021 11.30 AM | 01/09/2021 11.40 AM | Schedule AD_ACCESS_DEPROVISION_RECON and AD_REMOVE_ACCOUNT_90DAYS_RECON Job | KPMG | Anjali Patil/Ajinkya Chavan/ Sai Mulam | Pending